## Sheet1
|  |  | Sep ' 25 | [15 empty] | Oct '25 | [30 empty] | Nov '25 | [29 empty] | Dec ' 25 | [30 empty] | Jan '26 | [30 empty] | Feb '25 | [27 empty] | Mar '26 | [30 empty] | Apr ' 26 | [29 empty] | May '25
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33
|  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
AI and Solar Powered Grass Cutting Robot | START | END
Understand Project Requirements | 15/09/25 | 28/09/25 | bar: Week 1 15 to Week 2 28
Read Project Requirements | 15/09 | 17/09 | bar: Week 1 15 to Week 1 17
Initial Research | 15/09 | 28/09 | bar: Week 1 15 to Week 2 28
Select Project Title | 15/09 | 28/09 | bar: Week 1 15 to Week 2 28
Research | 29/0925 | 2025-10-12 | bar: Week 2 28 to Week 4 12
Study Equivalent Examples | 29/09 | 05/10 | bar: Week 2 28 to Week 3 5
Compare Components | 06/10 | 12/10 | bar: Week 4 6 to Week 4 12
Create List & Diagram | 13/10/25 | 26/10/25 | bar: Week 5 13 to Week 6 26
Components List | 13/10 | 19/10 | bar: Week 5 13 to Week 5 19
System Block Diagram | 20/10 | 26/10 | bar: Week 6 20 to Week 6 26
Software Tools & Flowchart | 27/10/25 | 2025-11-09 | bar: Week 7 27 to Week 8 9
Software Tools | 27/10 | 02/11 | bar: Week 7 27 to Week 7 2
Flowchart | 03/11 | 09/11 | bar: Week 8 3 to Week 8 9
Borrow Components | 2025-11-10 | 2025-11-23 | bar: Week 9 10 to Week 10 23
Email Lab To Borrow Compenents | 10/11 | 16/11 | bar: Week 9 10 to Week 9 16
Collect Items | 17/11 | 23/11 | bar: Week 10 17 to Week 10 23
Hardware Testing | 2025-11-24 | 2025-12-07 | bar: Week 11 24 to Week 12 7
Functional Testing | 24/11 | 30/11 | bar: Week 11 24 to Week 11 30
Power System Integration | 24/11 | 30/11 | bar: Week 11 24 to Week 11 30
Connection between Controller & Laptop | 01/12 | 07/12 | bar: Week 12 1 to Week 12 7
Holiday Break (Overseas Trip) | 2025-12-08 | 2026-01-04 | Week 13 9: Holiday Break (Overseas Trip)
Continue Hardware Testing | 2025-01-05 | 2025-01-18 | bar: Week 17 5 to Week 18 18
Connect Power System with Controller | 05/01 | 08/01 | bar: Week 17 5 to Week 17 8
Connect Actuators (Wheels, Motor Cutter) | 09/01 | 18/01 | bar: Week 17 9 to Week 18 18
Connect LCD Display | 09/01 | 18/01 | bar: Week 17 9 to Week 18 18
Sensors Integration | 2025-01-19 | 2025-02-01 | bar: Week 19 19 to Week 20 1
Connect RSP 32 CAM | 19/01 | 22/01 | bar: Week 19 19 to Week 19 22
Connect SG90 + HC-SR04 | 23/01 | 25/01 | bar: Week 19 23 to Week 19 25
Connect LIDAR | 26/01 | 01/02 | bar: Week 20 26 to Week 20 1
Charging Detection & Remote | 2025-02-02 | 2025-02-15 | bar: Week 21 2 to Week 22 15
Connect LDR sensor | 02/02 | 08/02 | bar: Week 21 2 to Week 21 8
Connect HC05 Bluetooth | 09/02 | 15/02 | bar: Week 22 9 to Week 22 15
Design Chassis | 2025-02-16 | 2025-03-01 | bar: Week 23 16 to Week 24 1
3D Drawing | 16/02 | 22/02 | bar: Week 23 16 to Week 23 22
3D Printing & Drilling & Mounting | 23/02 | 01/03 | bar: Week 24 23 to Week 24 1
Final Adjustment | 2025-03-02 | 2025-03-15 | bar: Week 25 2 to Week 26 15
Check Accuracy | 02/03 | 08/03 | bar: Week 25 2 to Week 25 8
Outdoor Testing | 09/03 | 15/03 | bar: Week 26 9 to Week 26 15
Report Writing | 2025-03-16 | 2025-03-29 | bar: Week 27 16 to Week 28 29
Prepare Report | 16/03 | 22/03 | bar: Week 27 16 to Week 27 22
Prepare PPT | 23/03 | 29/03 | bar: Week 28 23 to Week 28 29
Double Checking | 2025-03-30 | 2025-04-12 | bar: Week 29 30 to Week 30 12
Robot Checking | 30/03 | 05/04 | bar: Week 29 30 to Week 29 5
Report Checking | 06/04 | 12/04 | bar: Week 30 6 to Week 30 12
PPT Checking | 06/04 | 12/04 | bar: Week 30 6 to Week 30 12