## Updated Gantt Chart
AI and Solar Powered Grass Cutting Robot — Updated Project Gantt Chart | Student: Tan Qi Yuan ¦ ID: 031DDDDD ¦ Supervisor: Wong Kim Siong ¦ Submitted: 03 April 2026
✔ Completed | ~ Partial | ✗ Not Done | → In Progress | ● SD Card Fail | ◆ Holiday
Task | Status | Start | End | Sep '25 | [15 empty] | Oct '25 | [30 empty] | Nov '25 | [29 empty] | Dec '25 | [30 empty] | Jan '26 | [30 empty] | Feb '26 | [27 empty] | Mar '26 | [30 empty] | Apr '26
|  |  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
AI and Solar Powered Grass Cutting Robot | → In Progress | 15/09/25 | 2026-09-04
1. Project Understanding & Research | ✔ Complete | 15/09/25 | 28/09/25 | bar: Sep '25 15 to Sep '25 28
Read Project Requirements | ✔ Complete | 15/09/25 | 17/09/25 | bar: Sep '25 15 to Sep '25 17
Initial Research | ✔ Complete | 15/09/25 | 28/09/25 | bar: Sep '25 15 to Sep '25 28
Select Project Title | ✔ Complete | 15/09/25 | 28/09/25 | bar: Sep '25 15 to Sep '25 28
2. Research | ✔ Complete | 29/09/25 | 12/10/25 | bar: Sep '25 29 to Oct '25 12
Study Equivalent Examples | ✔ Complete | 29/09/25 | 05/10/25 | bar: Sep '25 29 to Oct '25 5
Compare Components | ✔ Complete | 06/10/25 | 12/10/25 | bar: Oct '25 6 to Oct '25 12
3. Create List & Diagram | ✔ Complete | 13/10/25 | 26/10/25 | bar: Oct '25 13 to Oct '25 26
Components List | ✔ Complete | 13/10/25 | 19/10/25 | bar: Oct '25 13 to Oct '25 19
System Block Diagram | ✔ Complete | 20/10/25 | 26/10/25 | bar: Oct '25 20 to Oct '25 26
4. Software Tools & Flowchart | ✔ Complete | 27/10/25 | 09/11/25 | bar: Oct '25 27 to Nov '25 9
Software Tools Selection | ✔ Complete | 27/10/25 | 02/11/25 | bar: Oct '25 27 to Nov '25 2
System Flowchart | ✔ Complete | 03/11/25 | 09/11/25 | bar: Nov '25 3 to Nov '25 9
5. Borrow Components | ✔ Complete | 10/11/25 | 23/11/25 | bar: Nov '25 10 to Nov '25 23
Email Lab to Borrow Components | ✔ Complete | 10/11/25 | 16/11/25 | bar: Nov '25 10 to Nov '25 16
Collect Items from Lab | ✔ Complete | 17/11/25 | 23/11/25 | bar: Nov '25 17 to Nov '25 23
6. Hardware Testing | ✔ Complete | 24/11/25 | 07/12/25 | bar: Nov '25 24 to Dec '25 7
Functional Testing of Components | ✔ Complete | 24/11/25 | 30/11/25 | bar: Nov '25 24 to Nov '25 30
Power System Integration | ✔ Complete | 24/11/25 | 30/11/25 | bar: Nov '25 24 to Nov '25 30
Raspberry Pi Connection & Remote Access | ✔ Complete | 01/12/25 | 07/12/25 | bar: Dec '25 1 to Dec '25 7
7. Holiday Break (Overseas Trip) | ◆ Holiday | 08/12/25 | 04/01/26 | bar: Dec '25 8 to Jan '26 4
8. Continue Hardware Testing | ✔ Complete | 05/01/26 | 2026-01-02 | bar: Jan '26 5 to Feb '26 1
Connect Power System with Controller | ✔ Complete | 05/01/26 | 2026-01-02 | bar: Jan '26 5 to Feb '26 1
Connect Actuators (Wheels, Motor Cutter) | ✔ Complete | 2026-10-01 | 18/01/26 | bar: Jan '26 19 to Feb '26 1
Connect LCD Display [NOT COMPLETED] | ✗ Not Done | 09/01/26 | 18/01/26 | bar: Jan '26 19 to Feb '26 1
9. Sensors Integration | ~ Partial | 19/01/26 | 01/02/26 | bar: Jan '26 19 to Feb '26 1
Connect Pi Camera Module 2 [NOT COMPLETED] | ~ Partial | 19/01/26 | 22/01/26 | bar: Jan '26 19 to Jan '26 22
Connect HC-SR04 Ultrasonic [NOT COMPLETED] | ✗ Not Done | 23/01/26 | 25/01/26 | bar: Jan '26 23 to Jan '26 25
Connect RPLidar A1M8 | ✔ Complete | 26/01/26 | 01/02/26 | bar: Jan '26 26 to Feb '26 1
10. SLAM Development | ~ Partial | 02/02/26 | 31/03/26 | bar: Feb '26 2 to Mar '26 26
Install ROS2 Kilted + RVIZ2 Packages | ✔ Complete | 02/02/26 | 24/02/26 | bar: Feb '26 2 to Feb '26 24
*** SD CARD FAILURE - REBUILD (2 weeks lost) *** | ● SD Card Failure Event | 10/02/26 | 24/02/26 | bar: Feb '26 10 to Feb '26 24
Teleop Control + LIDAR Scanning (Working) | ✔ Complete | 23/02/26 | 15/03/26 | bar: Feb '26 23 to Mar '26 15
Save SLAM Map | ✔ Complete | 16/03/26 | 31/03/26 | bar: Mar '26 12 to Mar '26 22
Navigate Algorithm Development [NOT COMPLETED] | ~ Partial | 01/03/26 | 15/03/26 | bar: Mar '26 1 to Mar '26 15
Autonomous Navigation [NOT COMPLETED] | ✗ Not Done | 09/03/26 | 31/03/26 | bar: Mar '26 9 to Mar '26 26
11. Charging Detection & Wireless | ✗ Not Done | 02/02/26 | 15/02/26 | bar: Feb '26 2 to Feb '26 15
Connect LDR Sensor [NOT COMPLETED] | ✗ Not Done | 02/02/26 | 08/02/26 | bar: Feb '26 2 to Feb '26 8
Connect HC-05 Bluetooth [NOT COMPLETED] | ✗ Not Done | 09/02/26 | 15/02/26 | bar: Feb '26 9 to Feb '26 15
12. Design & Build Chassis | ✔ Complete | 16/02/26 | 01/03/26 | bar: Feb '26 23 to Mar '26 1
3D Drawing (Online Design Adopted) | ✔ Complete | 23/02/26 | 25/02/26 | bar: Feb '26 23 to Feb '26 25
3D Printing & Drilling & Mounting & Assembly | ✔ Complete | 26/02/26 | 01/03/26 | bar: Feb '26 26 to Mar '26 1
13. Final Adjustment & Testing | ~ Partial | 02/03/26 | 24/03/26 | bar: Mar '26 2 to Mar '26 24
Check Accuracy / Speed Tuning [Not Completed] | ~ Partial | 02/03/26 | 24/03/26 | bar: Mar '26 2 to Mar '26 24
Indoor & Outdoor Testing [Not Completed] | ~ Partial | 2026-07-03 | 24/03/26 | bar: Mar '26 7 to Mar '26 24
14. Report Writing | ✔ Complete | 25/03/26 | 31/03/26 | bar: Mar '26 25 to Mar '26 31
Prepare Final Report | ✔ Complete | 25/03/26 | 2026-03-04 | bar: Mar '26 25 to Apr '26 3
Prepare Presentation Slides | → In Progress | 30/03/26 | 07/04/26 | bar: Mar '26 30 to Apr '26 7
15. Final Review & Submission | → In Progress | 30/03/26 | 07/04/26 | bar: Mar '26 30 to Apr '26 7
Robot & System Checking | → In Progress | 30/03/26 | 2026-09-04 | bar: Mar '26 30 to Apr '26 9
Report Final Check | ✔ Complete | 2026-01-04 | 2026-03-04 | bar: Apr '26 1 to Apr '26 3